## Risk Register
Risk Register
Project Detail | Online Thrifted Shoe Store
Risk Name | Risk Description | Likelihood | Impact | Severity | Risk Owner | Mitigation Action | Response Plan | Progress | Status | Remark
Inventory Mismanagement | Inaccurate stock records may cause selling items that are unavailable or wrong sizes. | 4 | 3 | 12 | Business Owner | Maintain updated Google Sheets stock log; verify stock after every purchase. | Mitigate | In Progress | Medium | Need automated stock update in future.
Delivey Delays/Lost Parcels | Delivery partners may delay or lose parcels, affecting customer trust. | 3 | 4 | 12 | Logistics Lead | Use reputable courier; track parcels daily; maintain backup courier. | Mitigate | Ongoing | Medium | Track daily and maintain customer communication.
Payment Fraud | Customers may send fake payment screenshots or refuse to pay on COD. | 3 | 5 | 15 | Business Owner | Verify all payments before shipping; partial advance for expensive pairs. | Mitigate | Implementing | High | Losses noted in previous orders, strict policy needed.
Social Media Account Hack | Instagram account may be hacked, resulting in loss of customers and data. | 3 | 5 | 15 | Business Owner | Turn on 2FA; use strong passwords; backup product photos. | Mitigate | In Progress | High | Add backup admin account
Custoimers Complaint | Custoimers may claim incorrect quality or size, damaging brand reputation | 4 | 3 | 12 | Customer Service Lead | Upload clear pictures; size verification; transparency in condition. | Mitigate | Improvising listing quality | Medium | Add size chart to each listing.
Supplier Reliabilty Risk | Suppliers may delay or deliver low-quality shoes affecting product availability. | 3 | 4 | 12 | Procurement Lead | Work with 2–3 reliable suppliers; verify stock quality on receipt. | Mitigate | Ongoing | Medium | Need quality checklist.
Negative Social Media Reviews | Bad reviews may impact sales and reputation significantly. | 2 | 4 | 8 | Business Owner | Promote customer satisfaction; respond to complaints; maintain transparency. | Mitigate | Ongoing | Medium | Plan to post customer testimonals weekly.
Data Loss (Chats/Orders) | Losing chat history due to device reset or app issues impacts order tracking. | 2 | 5 | 10 | Business Owner | Backup order database weekly; export customer addresses to Google Sheets. | Mitigate | Started | Medium | Need automated backup workflow.

## Sheet2 (hidden)
Risk Category | Risk Impact Area | Impact Scale | Likelihood/ Probability | Controllability
Health and safety | People | Incidental | Frequent (Up to once in 5 years (>1 to 0.2)) | Virtually avoidable
Environmental | Environment | Minor | Likely (Over once in 5 years up to once in 10 years (<0.2 to 0.1)) | Largely Controllable
Human resources | Project Objectives ((cost, quality, schedule, commercial) | Moderate | Possible (Over once in 10 years up to once in 25 years (<0.1 to 0.04)) | Partially Controllable
Contractual and legal | Company reputation (corporate image, external stakeholders). | Major | Unlikely (Over once in 25 years up to once in 100 years (<0.04 to 0.01)) | Laregely Uncontrollable
Credit/supplier risks |  | Severe | Rare (Over once in 100 years up to once in 1000 years (<0.01 to 0.001)) | Virtually Uncontrollable |  | , , , , , , , , , , , , , ,
Market |  |  | Very rare (Once in 1000 years or more (<0.001))
Financial
Model & validation
Subsurface
Operational | Risk Assessment |  |  |  | , minor, moderate, major, severe | People, environment, project objectives (cost, quality, schedule, commercial), Company reputation (corporate image, external stakeholders).
Political | Low
Regulatory | Medium
Reputation | High
Strategic | V.High
Technology