## Risk Register
Risk Register
Project Detail | Online Thrifted Shoe Store
Risk Name | Risk Description | Likelihood | Impact | Severity | Risk Owner | Mitigation Action | Response Plan | Progress | Status | Remark
Inventory Mismanagement | Inaccurate stock records may cause selling items that are unavailable or wrong sizes. | 4 | 3 | 12 | Business Owner | Maintain updated Google Sheets stock log; verify stock after every purchase. | Mitigate | In Progress | Medium | Need automated stock update in future.
Delivey Delays/Lost Parcels | Delivery partners may delay or lose parcels, affecting customer trust. | 3 | 4 | 12 | Logistics Lead | Use reputable courier; track parcels daily; maintain backup courier. | Mitigate | Ongoing | Medium | Track daily and maintain customer communication.
Payment Fraud | Customers may send fake payment screenshots or refuse to pay on COD. | 3 | 5 | 15 | Business Owner | Verify all payments before shipping; partial advance for expensive pairs. | Mitigate | Implementing | High | Losses noted in previous orders, strict policy needed.
0
0
0
0
0
0

## Sheet2 (hidden)
Risk Category | Risk Impact Area | Impact Scale | Likelihood/ Probability | Controllability
Health and safety | People | Incidental | Frequent (Up to once in 5 years (>1 to 0.2)) | Virtually avoidable
Environmental | Environment | Minor | Likely (Over once in 5 years up to once in 10 years (<0.2 to 0.1)) | Largely Controllable
Human resources | Project Objectives ((cost, quality, schedule, commercial) | Moderate | Possible (Over once in 10 years up to once in 25 years (<0.1 to 0.04)) | Partially Controllable
Contractual and legal | Company reputation (corporate image, external stakeholders). | Major | Unlikely (Over once in 25 years up to once in 100 years (<0.04 to 0.01)) | Laregely Uncontrollable
Credit/supplier risks |  | Severe | Rare (Over once in 100 years up to once in 1000 years (<0.01 to 0.001)) | Virtually Uncontrollable |  | , , , , , , , , , , , , , ,
Market |  |  | Very rare (Once in 1000 years or more (<0.001))
Financial
Model & validation
Subsurface
Operational | Risk Assessment |  |  |  | , minor, moderate, major, severe | People, environment, project objectives (cost, quality, schedule, commercial), Company reputation (corporate image, external stakeholders).
Political | Low
Regulatory | Medium
Reputation | High
Strategic | V.High
Technology